## Backlog
Backlog
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
1 |  | Developer | Know what language to use | I can work on the project | The language is decided | Beginning |  | Completed |  |  |  |  | 0
4 |  | Developer | Determine what development tools to use | I can work on the project | Tools are installed and usable | Beginning |  | Completed |  |  |  |  | 0
2 |  | Developer | Determine how client is charged | Compute Payments | Client is asked for correct amount | Middle |  | In progress |  |  |  |  | 3
3 |  | Developer | Determine what shows on the screen | I can keep track of what the program is doing | When payments are assessed, amount and the name of the client shows on screen | Front |  | In progress |  |  |  |  | 40
5 |  | Developer | Know what data we are going to store about the customer | I can write the software that stores and access the data | List of information we're storing about client is complete | Back |  | In progress |  |  |  |  | 2021-08-13
6 |  | Developer | Know what the format of the data is for the database | I can write code that puts data in the database and reads data from the database | Data has been written to and retrieved from database | Back |  | In progress |  |  |  |  | 20
7 |  | Developer | Store information about our clients | we can retrieve and process information as necessary | Data has been written to and retrieved from database | Back |  | In progress |  |  |  |  | 30
8 |  | Developer | I want to dissern what data to pass on to the database | So that it can be implemented | Data is acceptable to be stored in the database | Hypothetical |  | In progress
9 |  | Developer | Note the time clients are admitted in short-term parking | we can determine how much they should be charged | Store time admitted for calculating from start to finish | Middle |  | In progress
10 |  | Develeper | Keep track of total parking spaces | we know when we can admit clients | List available parking spaces | Middle/Back |  | In progress
11 |  | Developer | Use a system for configuration management | Work on a common development codebase without clobbering others work or introducing errors | CM system has been determined, developer has tried pulling commiting and pushing. |  |  | In progress

## Main
See | https://techformist.com/free-agile-scrum-excel-template
Scrum Project
Product | Parking Garage |  | Date | 20/Sept/21
Git | https://github.com/Shane-is-here/CS-275-Team-3 |  | Sprint # | 1
Team
Scrum Master | Shane McQuaid |  | Team # | 3
Developers | Brenden Reim
Michael Kates
Jacob Dunst
Kevin Hoffman
Epic | [5 empty] | Sprint Plan |  | CS275 Garage
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Scrum Master
1 | Platforms / GUI / Data | 20/Sept/21 | 2021-10-01 |  |  | Spr. 1.1 | 2021-09-20 | 2021-10-01 |  |  |  | Shane McQuaid
2 | Daily Customer Functionality |  |  |  |  | Spr. 1.2 | 2021-10-04 | 2021-10-15 |  |  |  | Brenden Reim
3 | Long Term Client Functionality |  |  |  |  | Spr. 1.3 | 2021-10-18 | 2021-10-29 |  |  |  | Michael Kates
[6 empty] | Spr. 1.4 | 2021-11-01 | 2021-11-12 |  |  |  | Jacob Dunst
[6 empty] | Spr. 1.5 | 2021-11-15 | 2021-11-26 |  |  |  | Kevin Hoffman
[6 empty] | Spr. 1.6 | 2021-11-29 | 2021-12-10 |  |  |  | Shane McQuaid
Formulas:
CS275 Garage = [Start]+11
Start = [CS275 Garage, row above]+3

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 | 1 |  | N/A | Completed | 0 | 0 | 0
1.1 | 2 | How client is charged | Shane McQuaid | In Progress | 3 | 0 | 3
1.1 | 3 | Determine what shows on the screen | Kevin Hoffman | In Progress | 3 | 0 | 3
1.1 | 4 |  | N/A | Completed | 0 | 0 | 0
1.1 | 5 |  | Michael Kates | In Progress | 3 | 0 | 3
1.1 | 6 |  | Michael Kates | In Progress | 5 | 0 | 5
1.1 | 7 |  | Michael Kates | In Progress | 5 | 0 | 5
1.1 | 8 | Data to pass on to database | Jacob Dunst | Completed |  | 0 | 0
1.1 | 9 | Get current date/time | Jacob Dunst |  |  | 0 | 0
1.1 | 10 | Plan and create garage structure | Brenden Reim | In Progress | 20 | 1.5 | 18.5 | 1 | 0.5
1.1 | 11 |  | Shane McQuaid | In Progress | 3 | 0 | 3
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 42 | 1.5 | 40.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Burn down |  |  |  | 41 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5
|  |  |  | Burn up |  |  |  | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms

## Shane TODO
TODO |  |  |  | Status | ETA
| Use a system for configuration management | Work on a common development codebase without clobbering others work or introducing errors | CM system has been determined, developer has tried pulling commiting and pushing. | In Progress | End of week
| Determine how client is charged | Compute Payments | Client is asked for correct amount | In Progress

## Mikes TODO Things
Da List | Status
Create data list for db reference | In Progress
Create method to write data into the db | In Progress
Create method to retrieve data from the db | In Progress
Clarify what data is being saved | In Progress

## Jacob TODO
To do |  |  | Status
I want to dissern what data to pass on to the database | So that it can be implemented | Data is acceptable to be stored in the database | In progress
Note the time clients are admitted in short-term parking | we can determine how much they should be charged | Store time admitted for calculating from start to finish | In progress

## Kevin TODO
Tasks
Sprint | Description | User Story/Task | Story Points (if applicable) | Status
1.1 | Determine what shows on the screen | User Story | 3 | Started
1.1 | Plan out screen for registration form for long term | Task | 4 | Started
1.1 | Design generalized format for displaying garage spot availability | Task | 4 | Started
1.1 | Research about the server-client model to connect an HTML5-based GUI to Java middleware | Task | 2 | Started

## Brenden TODO
Brenden TODO
| Tasks | Status
| Plan out what types of vehicles will be in the garage | In Progress
| Plan out what the parking garage will look like (conceptually) | In Progress
| Create classes for the types of Vehicles, with a Vehicle superclass | Not started
| Create a parking garage class | Not started