## Backlog
Backlog
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
1 |  | Developer | Know what language to use | I can work on the project | The language is decided | Beginning |  | Completed |  |  |  |  | 0
2 |  | Developer | Determine how client is charged | Compute Payments | Client is asked for correct amount | Middle |  | Completed |  |  |  |  | 3
3 |  | Developer | Determine what shows on the screen | I can keep track of what the program is doing | When payments are assessed, amount and the name of the client shows on screen | Front |  | Completed |  |  |  |  | 40
4 |  | Developer | Determine what development tools to use | I can work on the project | Tools are installed and usable | Beginning |  | Completed |  |  |  |  | 0
5 |  | Developer | Know what data we are going to store about the customer | I can write the software that stores and access the data | List of information we're storing about client is complete | Back |  | Completed |  |  |  |  | 2021-08-13
6 |  | Developer | Know what the format of the data is for the database | I can write code that puts data in the database and reads data from the database | Data has been written to and retrieved from database | Back |  | Completed |  |  |  |  | 20
7 |  | Developer | Store information about our clients | we can retrieve and process information as necessary | Data has been written to and retrieved from database | Back |  | Completed |  |  |  |  | 30
8 |  | Developer | I want to dissern what data to pass on to the database | So that it can be implemented | Data is acceptable to be stored in the database | Hypothetical |  | In progress
9 |  | Developer | Note the time clients are admitted in short-term parking | we can determine how much they should be charged | Store time admitted for calculating from start to finish | Middle |  | In progress
10 |  | Develeper | Keep track of total parking spaces | we know when we can admit clients | List available parking spaces | Middle/Back |  | In progress |  |  |  | 2
11 |  | Developer | Use a system for configuration management | Work on a common development codebase without clobbering others work or introducing errors | CM system has been determined, developer has tried pulling commiting and pushing. | Middle |  | In progress
12 | [7 empty] | Completed
13 |  | Developer | Create the methods regarding the functions the parking garage itself runs on | We can keep have functions to keep track of changes in the garage | Methods able to process and communicate data | Middle |  | Completed
14 |  | Developer | Distinguish between Daily and Long term users within the program | We will be able to implement accordingly | We have different classes for the Daily and Long Term users, each with their own methods | Middle |  | Completed
15 |  | Client | Change my account information | I am not stuck with old information | The client can change their contact info or payment plan from the GUI | Front/middle
16 |  | Client | Be assigned a parking spot | I can quickly park | User receives a random spot number/ID when they check in | Front/middle
17 |  | Client | View the pricing for different lengths of time | I can see how much I might end up paying, before I park | GUI has a section of garage pricing | Front |  | Completed
18 |  | Developer | Be able to communicate between the gui and in middleware | The flow of information is more clear | We have an interface between the front end and the middleware | Front/middle |  | Completed
19 | funny ha ha | Hacker | Access payment info | I make money fast | I get all the info | Don't call the police plz
20 |  | Developer | an easy way for the middleware save and retrieve data from the DB | Data can be easily saved an retrieved | We have an interface between the back end and the middleware | middle/back |  | In Progress
20.5 |  | Developer | Know what methods to have to fill in for said interface | I don't create methods that don't need to be created | An outline for the database has been created | Middle/Back |  | Completed
21 |  | Client | have multiple payment options | I can still park if I do not have a specific payment plan | At least 3 different payments plans (Paypal, credit, Apple Pay, etc.). | Front/middle
22 |  | Developer | I want to have a way to easily keep track of what spaces are taken | I can assign people spots that are not taken | Have functional Hash Map that keeps track | Middle
23 |  | Management | see daily reports of how many spots are taken and how much money was made per day | I can track how business is going | Display of cost, revenue, net cars, etc. | Middle
24 |  | Client | All of my information to be secure | my personal information is not stolen or leaked | User data is encrypted(?) in the database | Middle/back |  | Not Started
24.1 |  | Dev | Encrypt Passwords | even if the database is not secure, passwords are not leaked | we encrypt passwords :) | Middle/Back |  | Not Started
25 |  | Client | Retrieve forgotten account information | I do not lose access to my acount | Forgot my username/ID/password setting to reset info | Middle/back |  | Not Started
26 |  | Developer | Create a Java class for handling requests from the GUI | the GUI can interact with the middleware and the user classes | GUI request is handled and executed by the middleware | Front/middle |  | Completed
27 |  | Developer
28 |  | Management | count the cars going into and out of the garage | I can see the garage's activity | Global variables to track cars going in and cars going out. Easily accessible method to find both counts | Middle |  | Completed
29 |  | Developer | Send data from the GUI to the middleware | The data can be properly processed and stored in the database | Middleware active when GUI submits request | Front/Middle |  | Completed
30 |  | Client | Create an account | I have long-term parking options | GUI has option to create and view account details. Communicates with middleware for processing | Front/Middle |  | In Progress
31 |  | Developer | Send information from the middleware | Data about the garage system can be accessed by the rest of the program | Middleware posts data | Middle |  | In Progress
32 |  | Developer | allow the GUI to recieve data | The GUI can be updated about changes in the garage | GUI get method developed | Front |  | Completed
33 |  | Developer | Communicate the garage structure to the gui | the gui is able to display the available spots | the gui is able to access the Garage Hashmap | Front/Middle |  | In Progress
34 |  | Developer | Have the GUI call methods in the middleware | There is full functionality between the two parts of the program | GUI requests result in the corresponding methods in the middleware being called | Front/Middle |  | Completed
35 |  | Developer | Allow the user to login in to see acount details | we can confidently show sensitive data to the user about their account | The user is granted access if credentials exist, otherwise reenter details | Front |  | In Progress
36 |  | Developer | Verify account details | Check the database to see if account details are present | Identify if a given set of username/password or ID is in the database | Middle
37 |  | Developer | Display parking garage | the user can select a parkign spot for long-term parking | 2d visualization of parking lot showing what spots are available | Front |  | Complete
38 |  | Developer | Select parking spot in garage | users can secure their long-term parking | Send request to secure parking spot | Front |  | Complete
39 |  | Developer | Charge vehicles for the correct amount depending on the length they've been in the garage | They can pay the correct amount | we return the right amount the user owes | middle
40 |  | Developer | Determine the amount of time between two dates | We can determine the amount people owe after leaving the garage | the correct amount of time is returned when two dates are entered | middle
41 |  | Developer | Readjust our middleware to reflect the changes to out garage design | we are able to call the correct methods to calculate the correct information | we are able to post correct information to the gui | middle
42 |  | Developer | Move user data from the GUI to the database | We can pull user details later on when we need them | We are able to input data in the GUI and have it be saved in the DB | Middle/back |  | Completed
43 |  | Developer | Store and Retrieve the garage datastructure | We can have our information be saved when the program isnt running | we are able to store and retrieve the garage hashmap | back
44 |  | Developer | Finalize the information being pulled from the database and sent to the GUI | the gui can access all relevant information of specific users | user information can be posted to the gui
45 |  | Developer | Pull user data from the DB and send it to the GUI | users can view/edit their accounts | The "view" and "edit account" functions in the GUI show the user's data | All
46 |  | Developer | Display the user's saved ID in the GUI | users can know their personal ID that they will use | The middleware assigns and ID to a user and sends it to the GUI | Front
47 |  | Developer | Generate a user's ID | Each customer can be uniquely identified | Each new ID generated is different from the rest | Middle
48 |  | Client | See my total before I pay | I can verify the pricing is correct | Shows pricing total before pressing pay | Front
49 |  | Client | Double check my inputted information | I can verify the information I submitted is correctly linked to myself | Information review pop up | Front
50 |  | Developer | use consistent naming conventions within data structures (username-uname, phone number-pnum, etc.) | the middleware and GUI can write in the same “language" | Every piece of information uses the same keywords in datastructures to identify them | Front/Middle
51 |  | Developer | Use the ID inputted by the user to pull their info from the DB | The program can perform operations with that specific user's data | Using the ID from the GUI, we can pull the corresponding info from the DB and use it in other methods | Middle/back
52 |  | Developer | Be able to recreate a user out of a database | we are able to use the data we retrieve | we have a user we can call functions on
53
54
55

## Main
See | https://techformist.com/free-agile-scrum-excel-template
Scrum Project
Product | Parking Garage |  | Date | 2021-10-16
Git | https://github.com/Shane-is-here/CS-275-Team-3 |  | Sprint # | 2
Team
Scrum Master | Michael Kates |  | Team # | 3
Developers | Jacob Dunst
Kevin Hoffman
Shane McQuaid
Brenden Reim
Epic | [5 empty] | Sprint Plan |  | CS275 Garage
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Scrum Master
1 | Platforms / GUI / Data | 20/Sept/21 | 2021-10-01 |  |  | Spr. 1.1 | 2021-09-20 | 2021-10-01 |  |  |  | Shane McQuaid
2 | Daily Customer Functionality |  |  |  |  | Spr. 1.2 | 2021-10-04 | 2021-10-15 |  |  |  | Brenden Reim
3 | Long Term Client Functionality |  |  |  |  | Spr. 1.3 | 2021-10-18 | 2021-10-29 |  |  |  | Michael Kates
[6 empty] | Spr. 1.4 | 2021-11-01 | 2021-11-12 |  |  |  | Jacob Dunst
[6 empty] | Spr. 1.5 | 2021-11-15 | 2021-11-26 |  |  |  | Kevin Hoffman
[6 empty] | Spr. 1.6 | 2021-11-29 | 2021-12-10 |  |  |  | Shane McQuaid
Formulas:
CS275 Garage = [Start]+11
Start = [CS275 Garage, row above]+3

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 | 1 |  | N/A | Completed | 0 | 0 | 0
1.1 | 2 | How client is charged | Shane McQuaid | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 1
1.1 | 3 | Determine what shows on the screen | Kevin Hoffman | Completed | 3 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
1.1 | 4 |  | N/A | Completed | 0 | 0 | 0
1.1 | 5 | Know what data to store to DB | Michael Kates | Completed | 3 | 3 | 0 | 0 | 0 | 0.5 | 0 | 2.5 | 0 | 0
1.1 | 6 | Be able to store data to get and retrieve | Michael Kates | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0
1.1 | 7 | Store info about clients | Michael Kates | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0
1.1 | 8 | Data to pass on to database | Jacob Dunst | Completed | 1 | 1 | 0
1.1 | 9 | Get current date/time | Jacob Dunst |  | 1 | 1 | 0 |  | 1 | 1
1.1 | 10 | Plan and create garage structure | Brenden Reim | Completed | 17 | 17 | 0 | 1 | 1 | 2 | 2 | 0 | 3 | 3 | 2 | 3
1.1 | 11 | System for configuration Management | Shane McQuaid | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 0
1.2 | 29 | Send data from the GUI to the middleware | Kevin Hoffman | Completed | 8 | 8 | 0 | 1 | 1 | 0 | 3 | 1 | 0 | 2
1.2 | 17 | View the pricing for different lengths of time | Kevin Hoffman | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
1.2 | 13 | Create the methods regarding the functions the parking garage itself runs on | Shane McQuaid | Completed | 10 | 10 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 5 | 0 | 0
1.2 | 28 | count the cars going into and out of the garage | Shane McQuaid | Completed | 4 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0
1.2 | 20 | an easy way for the middleware save an retrieve data from the DB | Michael Kates | Moved | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 0
1.2 | 30 | Create an account | Kevin Hoffman | Completed | 5 | 5 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 2 | 0
1.2 | 26 | Create a Java class for handling requests from the GUI | Brenden Reim | Completed | 13 | 13 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 3 | 4 | 0 | 0
1.2 | 24 | All of my information to be secure | Michael Kates | Not started | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 25 | Retrieve forgotten account information | Michael Kates | Not started | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 10 | Keep track of parking spaces | Jacob Dunst | In Progress | 4 | 4 | 0
1.2 | 20.5 | Create the interface between the Garage and the database | Jacob Dunst | In Progress | 8 | 8 | 0
1.2 | [5 empty] | 0 | 0
1.3 | 35 | Allow the user to login in to see acount details | Kevin Hoffman | Complete | 7 | 7 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 2 | 1
1.3 | 38 | Select parking spot in garage | Kevin Hoffman | Complete | 4 | 4 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | 20 | an easy way for the middleware save and retrieve data from the DB | Michael Kates | Completed | 4 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0
1.3 | 37 | Display parking garage | Kevin Hoffman | Complete | 8 | 8 | 0 | 1 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1
1.3 | 34 | Have the GUI requests call methods in middleware | Brenden Reim | Completed | 7 | 7 | 0 | 1 | 1 | 0 | 2 | 1 | 1 | 1 | 0 | 0 | 0
1.3 | 24 | Secure the info being sent into the database | Shane McQuaid | In Progress | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | 25 | Retrieve forgotten info | Shane McQuaid | In Progress | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 |  | Verify user account info | Shane McQuaid | In Progress | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | 42 | Save user info from the GUI to the DB, using the DBInterface class | Brenden Reim | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
1.3 | 41 | block the spot the user chas chosen in the middleware | Jacob Dunst | Completed | 4 | 4 | 0
1.3 | 39 | We have determined how long the user is in the garage | Jacob Dunst | complete | 10 | 0 | 10
1.4 | 48 | See my total before I pay | Kevin Hoffman | Not Started | 8 | 0 | 8
1.4 | 49 | Double check my inputted information | Kevin Hoffman | Not Started | 5 | 0 | 5
1.4 | 50 | use similar keywords for pieces of information going around (e.g., email, phone number) | Kevin Hoffman | Not Started | 3 | 0 | 3
1.4 | 52 | Be able to recreate a user out of a database | Jacob Dunst | Not Started | 4 | 0 | 4
1.4 | [5 empty] | 0 | 0
1.4 | [5 empty] | 0 | 0
1.4 | [5 empty] | 0 | 0
1.4 | [5 empty] | 0 | 0
1.4 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
1.3 | [5 empty] | 0 | 0
|  |  |  | Total | 235 | 137 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0
|  |  |  | Burn down |  |  |  | 235 | 235 | 235 | 235 | 235 | 235 | 235 | 233 | 231 | 231
|  |  |  | Burn up |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms

## Shane TODO
TODO | I want to: | So that: | Acceptance Crit. | Status | ETA
| Use a system for configuration management | Work on a common development codebase without clobbering others work or introducing errors | CM system has been determined, developer has tried pulling commiting and pushing. | Completed | N/A
| Determine how client is charged | Compute Payments | Client is asked for correct amount | Completed | N/A
| Create the methods regarding the functions the parking garage itself runs on | We can keep have functions to keep track of changes in the garage | Methods able to process and communicate data | Completed | Before the end of the sprint
| count the cars going into and out of the garage | I can see the garage's activity | Global variables to track cars going in and cars going out. Easily accessible method to find both counts | Completed | Before the end of the sprint

## Mikes TODO Things
Da List | Status
Create data list for db reference | Completed
Create method to write data into the db | Completed
Create method to retrieve data from the db | Completed
Clarify what data is being saved | Completed
Bridge database methods with java or json | Cancelled
Export methods | Cancelled
Create method to save the garage array | Cancelled
Save Data Method | Completed
Retrieve Data Method | Completed
Temp Save Function | Completed
Middleware Call for DB | Completed

## Kevin TODO
Tasks
Sprint | Description | User Story/Task | Story Points (if applicable) | Status
1.1 | Determine what shows on the screen | User Story | 3 | Completed
1.1 | Plan out screen for registration form for long term | Task | 4 | Completed
1.1 | Design generalized format for displaying garage spot availability | Task | 4 | Completed
1.1 | Research about the server-client model to connect an HTML5-based GUI to Java middleware | Task | 4 | Completed
1.1 | Pick learning JavaFX or HTTP Requests | Task | 2 | Completed
1.2 | Send data from the GUI to the middleware | User Story | 8 | Completed
1.2 | View the pricing for different lengths of time | User Story | 2 | Completed
1.3 | Select parking spot in garage | User Story | 4 | Completed
1.3 | Display parking garage | User Story | 8 | Completed
1.3 | Allow the user to login in to see acount details | User Story | 7 | Completed

## Jacob TODO
To do |  |  | Status
I want to dissern what data to pass on to the database | So that it can be implemented | Data is acceptable to be stored in the database | Done
Note the time clients are admitted in short-term parking | we can determine how much they should be charged | Store time admitted for calculating from start to finish | Done
Keep track of total parking spaces | we know when we can admit clients | List available parking spaces | In Progress
Know what methods to have to fill in for said interface | I don't create methods that don't need to be created | An outline for the database has been created | In Progress
33 | Developer | Communicate the garage structure to the gui | the gui is able to display the available spots | the gui is able to access the Garage Hashmap | Front/Middle
39 | Developer | Charge vehicles for the correct amount depending on the length they've been in the garage | They can pay the correct amount | we return the right amount the user owes | middle
40 | Developer | Determine the amount of time between two dates | We can determine the amount people owe after leaving the garage | the correct amount of time is returned when two dates are entered | middle

## Brenden TODO
Brenden TODO
| Tasks | Status
| Plan out what the parking garage will look like (conceptually) | Complete
| Create classes for the two types of users | Complete
| Create a class to handle requests from the GUI | Complete
| Create some code logic to call methods based on information sent from the GUI | Complete
| Get the "check-in" and "register" operations to work | Complete
| Get the "view", "check-out", and "edit" functions to work | In progress
| Transfer user data from the GUI to the DB | Complete
Checkout method steps:
Take in the ID, payment info, and timeOut from the GUI
Use the ID to pull the timeIn from the DB
Calculate the amount owed by using the timeIn and timeOut
Send the amount owed to the GUI