## Backlog
Backlog
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
1 |  | Developer | Know what language to use | I can work on the project | The language is decided | Beginning |  | Completed |  |  |  |  | 0
2 |  | Developer | Determine how client is charged | Compute Payments | Client is asked for correct amount | Middle |  | Completed |  |  |  |  | 3
3 |  | Developer | Determine what shows on the screen | I can keep track of what the program is doing | When payments are assessed, amount and the name of the client shows on screen | Front |  | Completed |  |  |  |  | 40
4 |  | Developer | Determine what development tools to use | I can work on the project | Tools are installed and usable | Beginning |  | Completed |  |  |  |  | 0
5 |  | Developer | Know what data we are going to store about the customer | I can write the software that stores and access the data | List of information we're storing about client is complete | Back |  | Completed |  |  |  |  | 2021-08-13
6 |  | Developer | Know what the format of the data is for the database | I can write code that puts data in the database and reads data from the database | Data has been written to and retrieved from database | Back |  | Completed |  |  |  |  | 20
7 |  | Developer | Store information about our clients | we can retrieve and process information as necessary | Data has been written to and retrieved from database | Back |  | Completed |  |  |  |  | 30
8 |  | Developer | I want to dissern what data to pass on to the database | So that it can be implemented | Data is acceptable to be stored in the database | Hypothetical |  | In progress
9 |  | Developer | Note the time clients are admitted in short-term parking | we can determine how much they should be charged | Store time admitted for calculating from start to finish | Middle |  | In progress
10 |  | Develeper | Keep track of total parking spaces | we know when we can admit clients | List available parking spaces | Middle/Back |  | In progress |  |  |  | 2
11 |  | Developer | Use a system for configuration management | Work on a common development codebase without clobbering others work or introducing errors | CM system has been determined, developer has tried pulling commiting and pushing. | Middle |  | In progress
12 | [7 empty] | Completed
13 |  | Developer | Create the methods regarding the functions the parking garage itself runs on | We can keep have functions to keep track of changes in the garage | Methods able to process and communicate data | Middle |  | Completed
14 |  | Developer | Distinguish between Daily and Long term users within the program | We will be able to implement accordingly | We have different classes for the Daily and Long Term users, each with their own methods | Middle |  | Completed
15 |  | Client | Change my account information | I am not stuck with old information | The client can change their contact info or payment plan from the GUI | Front/middle
16 |  | Client | Be assigned a parking spot | I can quickly park | User receives a random spot number/ID when they check in | Front/middle
17 |  | Client | View the pricing for different lengths of time | I can see how much I might end up paying, before I park | GUI has a section of garage pricing | Front |  | Completed
18 |  | Developer | Be able to communicate between the gui and in middleware | The flow of information is more clear | We have an interface between the front end and the middleware | Front/middle |  | Completed
19 | funny ha ha | Hacker | Access payment info | I make money fast | I get all the info | Don't call the police plz
20 |  | Developer | an easy way for the middleware save an retrieve data from the DB | Data can be easily saved an retrieved | We have an interface between the back end and the middleware | middle/back |  | In Progress
20.5 |  | Developer | Know what methods to have to fill in for said interface | I don't create methods that don't need to be created | An outline for the database has been created | Middle/Back |  | Completed
21 |  | Client | have multiple payment options | I can still park if I do not have a specific payment plan | At least 3 different payments plans (Paypal, credit, Apple Pay, etc.). | Front/middle
22 |  | Developer | I want to have a way to easily keep track of what spaces are taken | I can assign people spots that are not taken | Have functional Hash Map that keeps track | Middle
23 |  | Management | see daily reports of how many spots are taken and how much money was made per day | I can track how business is going | Display of cost, revenue, net cars, etc. | Middle
24 |  | Client | All of my information to be secure | my personal information is not stolen or leaked | User data is encrypted(?) in the database | Middle/back |  | Not Started
24.1 |  | Dev | Encrypt Passwords | even if the database is not secure, passwords are not leaked | we encrypt passwords :) | Middle/Back |  | Not Started
25 |  | Client | Retrieve forgotten account information | I do not lose access to my acount | Forgot my username/ID/password setting to reset info | Middle/back |  | Not Started
26 |  | Developer | Create a Java class for handling requests from the GUI | the GUI can interact with the middleware and the user classes | GUI request is handled and executed by the middleware | Front/middle |  | Completed
27 |  | Developer
28 |  | Management | count the cars going into and out of the garage | I can see the garage's activity | Global variables to track cars going in and cars going out. Easily accessible method to find both counts | Middle |  | Completed
29 |  | Developer | Send data from the GUI to the middleware | The data can be properly processed and stored in the database | Middleware active when GUI submits request | Front/Middle |  | Completed
30 |  | Client | Create an account | I have long-term parking options | GUI has option to create and view account details. Communicates with middleware for processing | Front/Middle |  | In Progress
31 |  | Developer | Send information from the middleware | Data about the garage system can be accessed by the rest of the program | Middleware posts data | Middle |  | In Progress
32 |  | Developer | allow the GUI to recieve data | The GUI can be updated about changes in the garage | GUI get method developed | Front |  | In Progress
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55

## Main
See | https://techformist.com/free-agile-scrum-excel-template
Scrum Project
Product | Parking Garage |  | Date | 2021-10-16
Git | https://github.com/Shane-is-here/CS-275-Team-3 |  | Sprint # | 2
Team
Scrum Master | Brenden Reim |  | Team # | 3
Developers | Michael Kates
Jacob Dunst
Kevin Hoffman
Shane McQuaid
Epic | [5 empty] | Sprint Plan |  | CS275 Garage
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Scrum Master
1 | Platforms / GUI / Data | 20/Sept/21 | 2021-10-01 |  |  | Spr. 1.1 | 2021-09-20 | 2021-10-01 |  |  |  | Shane McQuaid
2 | Daily Customer Functionality |  |  |  |  | Spr. 1.2 | 2021-10-04 | 2021-10-15 |  |  |  | Brenden Reim
3 | Long Term Client Functionality |  |  |  |  | Spr. 1.3 | 2021-10-18 | 2021-10-29 |  |  |  | Michael Kates
[6 empty] | Spr. 1.4 | 2021-11-01 | 2021-11-12 |  |  |  | Jacob Dunst
[6 empty] | Spr. 1.5 | 2021-11-15 | 2021-11-26 |  |  |  | Kevin Hoffman
[6 empty] | Spr. 1.6 | 2021-11-29 | 2021-12-10 |  |  |  | Shane McQuaid
Formulas:
CS275 Garage = [Start]+11
Start = [CS275 Garage, row above]+3

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 | 1 |  | N/A | Completed | 0 | 0 | 0
1.1 | 2 | How client is charged | Shane McQuaid | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 1
1.1 | 3 | Determine what shows on the screen | Kevin Hoffman | Completed | 3 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
1.1 | 4 |  | N/A | Completed | 0 | 0 | 0
1.1 | 5 | Know what data to store to DB | Michael Kates | Completed | 3 | 3 | 0 | 0 | 0 | 0.5 | 0 | 2.5 | 0 | 0
1.1 | 6 | Be able to store data to get and retrieve | Michael Kates | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0
1.1 | 7 | Store info about clients | Michael Kates | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0
1.1 | 8 | Data to pass on to database | Jacob Dunst | Completed | 1 | 1 | 0
1.1 | 9 | Get current date/time | Jacob Dunst |  | 1 | 1 | 0 |  | 1 | 1
1.1 | 10 | Plan and create garage structure | Brenden Reim | Completed | 17 | 17 | 0 | 1 | 1 | 2 | 2 | 0 | 3 | 3 | 2 | 3
1.1 | 11 | System for configuration Management | Shane McQuaid | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 0
1.2 | 29 | Send data from the GUI to the middleware | Kevin Hoffman | Completed | 8 | 8 | 0 | 1 | 1 | 0 | 3 | 1 | 0 | 2
1.2 | 17 | View the pricing for different lengths of time | Kevin Hoffman | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
1.2 | 13 | Create the methods regarding the functions the parking garage itself runs on | Shane McQuaid | Completed | 10 | 10 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 5 | 0 | 0
1.2 | 28 | count the cars going into and out of the garage | Shane McQuaid | Completed | 4 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 2 | 0
1.2 | 20 | an easy way for the middleware save an retrieve data from the DB | Michael Kates | In Progress | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 0
1.2 | 30 | Create an account | Kevin Hoffman | Completed | 5 | 5 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 2 | 0
1.2 | 26 | Create a Java class for handling requests from the GUI | Brenden Reim | Completed | 13 | 13 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 3 | 4 | 0 | 0
1.2 | 24 | All of my information to be secure | Michael Kates | Not started | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 25 | Retrieve forgotten account information | Michael Kates | Not started | 17 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | 10 | Keep track of parking spaces | Jacob Dunst | In Progress | 4 | 4 | 0
1.2 | 20.5 | Create the interface between the Garage and the database | Jacob Dunst | In Progress | 8 | 8 | 0
1.2 | [5 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 137 | 99 | 38 | 3 | 7 | 7.5 | 20 | 9.5 | 9 | 8 | 15 | 8 | 0
|  |  |  | Burn down |  |  |  | 134 | 127 | 119.5 | 99.5 | 90 | 81 | 73 | 58 | 50 | 50
|  |  |  | Burn up |  |  |  | 3 | 10 | 17.5 | 37.5 | 47 | 56 | 64 | 79 | 87 | 87

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms

## Shane TODO
TODO | I want to: | So that: | Acceptance Crit. | Status | ETA
| Use a system for configuration management | Work on a common development codebase without clobbering others work or introducing errors | CM system has been determined, developer has tried pulling commiting and pushing. | Completed | N/A
| Determine how client is charged | Compute Payments | Client is asked for correct amount | Completed | N/A
| Create the methods regarding the functions the parking garage itself runs on | We can keep have functions to keep track of changes in the garage | Methods able to process and communicate data | Not Started | Before the end of the sprint
| count the cars going into and out of the garage | I can see the garage's activity | Global variables to track cars going in and cars going out. Easily accessible method to find both counts | Not Started | Before the end of the sprint

## Mikes TODO Things
Da List | Status
Create data list for db reference | Completed
Create method to write data into the db | Completed
Create method to retrieve data from the db | Completed
Clarify what data is being saved | Completed
Bridge database methods with java or json | Cancelled
Export methods | Cancelled
Create method to save the garage array | Cancelled
Java to Json | In Progress

## Kevin TODO
Tasks
Sprint | Description | User Story/Task | Story Points (if applicable) | Status
1.1 | Determine what shows on the screen | User Story | 3 | Completed
1.1 | Plan out screen for registration form for long term | Task | 4 | Completed
1.1 | Design generalized format for displaying garage spot availability | Task | 4 | Completed
1.1 | Research about the server-client model to connect an HTML5-based GUI to Java middleware | Task | 4 | Completed
1.1 | Pick learning JavaFX or HTTP Requests | Task | 2 | Completed
1.2 | Send data from the GUI to the middleware | User Story | 8 | Completed
1.2 | View the pricing for different lengths of time | User Story | 2 | Completed
1.2 | Create an account | User Story | 5 | Completed

## Jacob TODO
To do |  |  | Status
I want to dissern what data to pass on to the database | So that it can be implemented | Data is acceptable to be stored in the database | Done
Note the time clients are admitted in short-term parking | we can determine how much they should be charged | Store time admitted for calculating from start to finish | Done
Keep track of total parking spaces | we know when we can admit clients | List available parking spaces | In Progress
Know what methods to have to fill in for said interface | I don't create methods that don't need to be created | An outline for the database has been created | In Progress

## Brenden TODO
Brenden TODO
| Tasks | Status
| Plan out what the parking garage will look like (conceptually) | Complete
| Create classes for the two types of users | Complete
| Create a class to handle requests from the GUI | Complete
| Create some code logic to call methods based on information sent from the GUI | In progress